## Sheet1
Project Planning - KubeWatch
|  |  | KW08 | KW09 | KW10 | KW11 | KW12 | KW13 | KW14 | KW15 | KW16 | KW17 | KW18 | KW19 | KW20 | KW21 | KW22
|  |  | SW01 | SW02 | SW03 | SW04 | SW05 | SW06 | SW07 |  | SW08 | SW09 | SW10 | SW11 | SW12 | SW13 | SW14
|  |  | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30
|  |  |  | M1 |  | M2 |  | M3 |  |  | M4 |  | M5 |  |  |  | M6
| 1 | Business Modelling
| 1.1 | Rough Project Plan (RUD)
| 1.2 | Detailed Project Plan (Scrum)
| 1.3 | Meeting Plan
| 2 | Requirements
| 2.1 | Non Functional Requirements | bar: 2022-05-23
| 2.2 | Functional Requirements | bar: 2022-02-28 to 2022-03-14; 2022-04-04 to 2022-04-11
| 3 | Design
| 3.1 | Kubernetes Cluster
| 3.2 | Dashboard
| 4 | Implementation
| 4.1 | Epic: User management | bar: 2022-04-04 to 2022-04-18
| 4.2 | Epic: Data visualisation | bar: 2022-04-04 to 2022-04-11
| 4.3 | Epic: Notification | bar: 2022-03-21 to 2022-03-28
| 4.4 | Epic: Cluster visualisation
| 4.5 | Epic: Cluster configuration | bar: 2022-05-02 to 2022-05-16
| 5 | Test
| 5.1 | Epic: User management | bar: 2022-04-04 to 2022-04-25
| 5.2 | Epic: Data visualisation | bar: 2022-03-21 to 2022-04-11
| 5.3 | Epic: Notification | bar: 2022-03-21 to 2022-04-11
| 5.4 | Epic: Cluster visualisation | bar: 2022-04-11 to 2022-05-02
| 5.5 | Epic: Cluster configuration | bar: 2022-04-11 to 2022-05-02
| 5.7 | Integration Test | bar: 2022-04-04 to 2022-05-09
| 6 | Deployment
| 6.1 | K8s Cluster and Website combination
| 7 | Configuration & Change Management
| 7.1 | Update Documentation
| 7.2 | Change requirements
| 8 | Project Management
| 8.1 | Time Tracking
| 8.2 | Current Task State
| 8.3 | Meeting Notes
| 8.4 | Risk Management
| 9 | Environment
| 9.1 | Tooling setup
| 9.2 | Repository setup
| 9.3 | CI/CD setup
| 9.4 | Test environment setup
| 9.5 | Continuous improvement
|  | Milestones: | 2022-02-21: Legend:
|  | M1: Project Plan | 2022-02-21: Inception
|  | M2: Requirements | 2022-02-21: Elaboration
|  | M3: End of Elaboration & Arch. Prototype | 2022-02-21: Construction
|  | M4: Quality | 2022-02-21: Transition
|  | M5: Architecture | 2022-02-21: Spring Holidays
M6: Project Presentation
Instructions for producing a PNG:
Windows
1. Highlight all relevant cells (A1:R56)
2. Open Paint :)
3. Paste content
4. Save as png
Linux
tbd