## Sheet1
Project Planning - KubeWatch
|  | KW08 | KW09 | KW10 | KW11 | KW12 | KW13 | KW14 | KW15 | KW16 | KW17 | KW18 | KW19 | KW20 | KW21 | KW22
|  | SW01 | SW02 | SW03 | SW04 | SW05 | SW06 | SW07 |  | SW08 | SW09 | SW10 | SW11 | SW12 | SW13 | SW14
|  | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30
|  |  | M1 |  | M2 |  | M3 |  |  | M4 |  | M5 |  | M6 |  | M7
1 | Business Modelling
1.1 | Rough Project Plan (RUD) | bar: 2022-02-21 to 2022-03-28; 2022-04-11
1.2 | Detailed Project Plan (Scrum) | bar: 2022-02-28 to 2022-05-23
1.3 | Meeting Plan | bar: 2022-02-28 to 2022-03-21; 2022-04-11
2 | Requirements
2.1 | Non Functional Requirements | bar: 2022-02-28 to 2022-03-14; 2022-04-04 to 2022-04-18; 2022-05-02; 2022-05-16 to 2022-05-23
2.2 | Functional Requirements | bar: 2022-02-28 to 2022-03-14; 2022-04-04 to 2022-04-18; 2022-05-02; 2022-05-16 to 2022-05-23
3 | Design
3.1 | Kubernetes Cluster | bar: 2022-02-28 to 2022-04-11
3.2 | Dashboard | bar: 2022-03-07 to 2022-05-23
4 | Implementation
4.1 | Epic: User management | bar: 2022-04-11; 2022-05-09 to 2022-05-16
4.2 | Epic: Data visualisation | bar: 2022-03-21 to 2022-04-18
4.3 | Epic: Notification | bar: 2022-04-04 to 2022-04-18; 2022-05-09 to 2022-05-16
4.4 | Epic: Cluster visualisation | bar: 2022-04-11; 2022-04-25 to 2022-05-02
4.5 | Epic: Cluster configuration | bar: 2022-04-11; 2022-05-09 to 2022-05-16
5 | Test
5.1 | Epic: User management | bar: 2022-04-11; 2022-05-09 to 2022-05-23
5.2 | Epic: Data visualisation | bar: 2022-03-28 to 2022-04-18; 2022-05-23
5.3 | Epic: Notification | bar: 2022-04-04 to 2022-04-18; 2022-05-09 to 2022-05-23
5.4 | Epic: Cluster visualisation | bar: 2022-04-11; 2022-04-25 to 2022-05-02; 2022-05-23
5.5 | Epic: Cluster configuration | bar: 2022-04-11; 2022-05-09 to 2022-05-23
5.7 | Integration Test | bar: 2022-04-04 to 2022-05-30
6 | Deployment
6.1 | K8s Cluster and Website combination | bar: 2022-03-14 to 2022-05-30
7 | Configuration & Change Management
7.1 | Update Documentation
7.2 | Change requirements | bar: 2022-03-14 to 2022-05-16
8 | Project Management
8.1 | Time Tracking
8.2 | Current Task State
8.3 | Meeting Notes
8.4 | Risk Management
9 | Environment
9.1 | Tooling setup | bar: 2022-02-21 to 2022-03-28; 2022-04-11
9.2 | Repository setup | bar: 2022-02-21 to 2022-03-07; 2022-04-11
9.3 | CI/CD setup | bar: 2022-03-14 to 2022-04-18
9.4 | Test environment setup | bar: 2022-03-28 to 2022-04-18; 2022-05-16 to 2022-05-23
9.5 | Continuous improvement
Milestones: |  | 2022-02-21: Legend:
M1: Project Plan |  | 2022-02-21: Inception
M2: Requirements |  | 2022-02-21: Elaboration
M3: End of Elaboration & Arch. Prototype |  | 2022-02-21: Construction
M4: Quality |  | 2022-02-21: Transition
M5: Architecture |  | 2022-02-21: Spring Holidays
M6: End of Implementation
M7: Project Presentation
Instructions for producing a PNG:
Windows
1. Highlight all relevant cells (A1:Q54)
2. Open Paint :)
3. Paste content
4. Save as png
Linux
1. Highlight all relevant cells (A1:Q54)
2. File → Export…
3. Select PNG as file format (bottom right)
4. Select ‘Selection’ (bottom left)
5. Click ‘Save’
6. Keep default options