## time_tracking_issues
iid	title	spent	total_estimate	(empty)
1	Update README.md	15m	15m
10	Advisor Meeting Thu 24.02.22	2h 30m	5h
11	Advisor Meeting Tue 01.03.22	2h 30m	5h
12	Model Architecture	1h 30m	4h
13	Document how we implement Scrum	30m	30m
16	FR7 - Send notifications by email	(empty)	(empty)
21	Evaluating Project Backlog / Sprint Backlog Solution	45m	1h
22	Preparation for Advisor Meeting Tue 01.03.22	(empty)	1h
23	Improve Kubernetes Guidelines	1h 45m	1h 30m
24	Add Trigger for Documentation Jobs in Pipline	1h 15m	1h
25	Documentation Setup	30m	30m
26	Create RUD (Grobplanung)	3h 30m	3h
27	Interface between K8 Cluster and GitLab-OST	6h	5h
28	Improve .gitignore to stop uploads of unnecessary local latex build files	30m	30m
29	Initial Threat Model	6h	5h
31	Review M1 document	2h 45m	1d
32	Set up web app	3h	2h
35	Set up automated time tracking reporting	3h	3h
36	Evalutating Local Kubernetes Dev environment solution	2d 4h	1d 6h
37	Fix and reactivate build_doc_diff job	30m	15m
38	Access to Documentation via permalink broken	15m	15m
39	Internal Meeting Mon 07.03.22	5h	5h
4	Internal Meeting Mon 28.02.22	5h	5h
40	Update Documentation with Git Workflow	30m	30m
41	Define Epics and User story	1d 30m	7h 45m
48	CI/CD Pipeline	45m	30m
49	Setup Database	(empty)	(empty)
5	Setup Gitlab Repository	15m	30m
50	Basic styling for UI	(empty)	(empty)
52	FR12 - User Defined Cluster Configuration	(empty)	(empty)
53	FR10 - Generation of network graphs from hard coded data	(empty)	(empty)
54	FR11 - Generation of network graphs from K8s Cluster	(empty)	(empty)
55	FR6 - Display notifications on UI	(empty)	(empty)
57	FR8 - Notifications to multiple mail addresses	(empty)	(empty)
58	FR9 - Notifications via other communication channels	(empty)	(empty)
59	FR5 - Customizable Dashboard	(empty)	(empty)
6	Assign all Roles	15m	15m
61	FR2 - Hard coded authentication	1h	(empty)
62	FR1 - Soft coded authentication	(empty)	(empty)
63	Review Meeting Tue 08.03.22	1h 30m	5h
65	Create domain model	1d 4h	6h
67	Internal Meeting Mon 14.03.22	5h	5h
68	Document NFRs	1h 15m	2h
69	Update Time Tracking	1h 30m	1h
7	Internal Meeting Tue 22.02.22	5h	5h
70	Refine FRs with highest priority	1h 10m	30m
71	Define process to refine FRs with lower priority	15m	30m
72	Update risk matrix and layout	3h 20m	3h
73	Implement feedback from review 1	1h 50m	2h
74	Set up automated time tracking with Markdown and Diagrams	1h 30m	2h
75	Webstorm project cleanup	2h	3h
76	Risk matrix updating guide and cleanup	(empty)	1h 30m
77	Create Wireframe	45m	30m
78	FR3 - Static Dashboard	(empty)	(empty)
79	FR4 - Add dynamic Charts	(empty)	(empty)
8	Create Risk Matrix	2h 15m	2h
80	Advisor Meeting Tue 15.03.22	5h	5h
81	Epcis and Personas description	1h 30m	2h
82	Prometheus Architecture	(empty)	(empty)
83	Run app locally with connection to local Kubernetes cluster	(empty)	(empty)
84	Finalise M2 document	1h	5h
86	Set up my local Kubernetes dev env	(empty)	2h
9	Finalise notes for Internal Meeting Mon 28.02.22	(empty)	30m
Total Result

## M1
Team member	Time spent
Petra Heeb	8.25h
Jan Untersander	7h
Benjamin Plattner	9.75h
Olivier Lischer	11.25h
Pascal Lehmann	8.5h

## M2
Team member	Time spent
Petra Heeb	8.25h
Jan Untersander	7h
Benjamin Plattner	9.75h
Olivier Lischer	11.25h
Pascal Lehmann	8.5h