## Sheet1
Project Planning - KubeWatch
Legende:
|  | KW08 | KW09 | KW10 | KW11 | KW12 | KW13 | KW14 | KW15 | KW16 | KW17 | KW18 | KW19 | KW20 | KW21 | KW22 | Inception
|  | SW01 | SW02 | SW03 | SW04 | SW05 | SW06 | SW07 |  | SW08 | SW09 | SW10 | SW11 | SW12 | SW13 | SW14 | Elaboration
| Milestones | KW09: M1; KW11: M2; KW13: M3; KW16: M4; KW18: M5; KW22: M6
| Business Modelling | [15 empty] | Construction
Rough Project Plan (RUD)
Detailled Porject Plan (Scrum)
Meeting Plan
| Requirements | [15 empty] | Transition
Mandatory Requirements
Optional Requirements
| Design | [15 empty] | Spring Holidays
Kubernetes Cluster
Website
| Implementation | [15 empty] | Milestones:
| K8's Cluster (Local) | [15 empty] | M1: Project Plan
| K8's Cluster (Server) | [15 empty] | M2: Requirements
| K8's Cluster (GitLab) | [15 empty] | M3: End of Elaboration & Arch. Prototype
| K8's Cluster (Functionality) | [15 empty] | M4: Quality
| Website (GitLab) | [15 empty] | M5: Architecture
| Website (Functionality) | [15 empty] | M6: Project Presentation
Test
K8's Local Cluster Implementation
K8's Server Cluster Implementation
K8's GitLab Implementation
K8's Cluster Functionality
Website GitLab Implementation
Website Functionality
Integration Test
Deployment
K8's Cluster and Website combination
Configuration & Change Management
Änderungsanforderungen
Project Management
Time Tracking
Current Task State
Meeting Notes
Risk Management
Environment