## Pivot Table_Sheet1_1
iid	title	spent	total_estimate	(empty)
1	Update README.md	15m	15m
10	Advisor Meeting Thu 24.02.22	2h 30m	5h
11	Advisor Meeting Tue 01.03.22	2h 30m	5h
12	Model Architecture	1h 30m	(empty)
13	Document how we implement Scrum	30m	30m
14	Setup Kuberentes	(empty)	(empty)
15	Collect Metrics Data from Kuberentes	(empty)	(empty)
16	Send Altert Notification	(empty)	(empty)
19	My Test Project Backlog Issue	(empty)	(empty)
20	My Sprint Backlog Issue	(empty)	(empty)
21	Evaluating Project Backlog / Sprint Backlog Solution	45m	1h
22	Meeting with advisor on 1/3/22 - preparation and minutes	(empty)	1h
23	Improve Kubernetes Guidelines	1h 45m	1h 30m
24	Add Trigger for Documentation Jobs in Pipline	30m	1h
25	Documentation Setup	30m	30m
26	Create RUD (Grobplanung)	2h 30m	3h
27	Interface between K8 Cluster and GitLab-OST	1h	2h
28	Improve .gitignore to stop uploads of unnecessary local latex build files	30m	30m
29	Initial Threat Model	6h	5h
31	Review M1 document	45m	1d
32	Set up web app	3h	2h
34	Test4567	(empty)	(empty)
4	Internal Meeting Mon 28.02.22	5h	5h
5	Setup Gitlab Repository	15m	30m
6	Assign all Roles	15m	15m
7	Internal Meeting Tue 22.02.22	5h	5h
8	Create Risk Matrix	2h	2h
9	Meeting 28.2. post processing	(empty)	30m
Total Result